## Report
SKANDA's E-Commerce Website
Earned Value Analysis Report
| Prepared By: | Adithya Narasinghe | [7 empty] | © 2012-2017 Vertex42 LLC
| Date: | 2022-03-23
[42]
| For Period: | Week 7
Summary:
This is the EV analysis report for the SKANDA E-Commerce Website project as of week five. After the project is completed, the final EV analysis report will be released.
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Domain Purchasing | 5000 | 0 | 0 | 0 | 5000 | 0 | 0 | 0
2 | Client Requirement | 6750 | 1500 | 1500 | 1500 | 1500 | 0 | 375 | 375
3 | Purchasing a WordPress template | 12000 | 0 | 0 | 0 | 0 | 12000 | 0 | 0
4 | Purchasing a hosting service and payment gateway | 43880 | 0 | 0 | 0 | 8000 | 0 | 0 | 35880
5 | Content Writing | 9000 | 0 | 0 | 3000 | 0 | 0 | 3000 | 3000
6 | Web Design | 28000 | 0 | 0 | 0 | 3000 | 5000 | 10000 | 10000
7 | Graphic Design | 14000 | 0 | 0 | 2000 | 0 | 0 | 6000 | 6000
8 | Final Review | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insert new rows above this one | [9 empty] | ← To add more tasks, insert rows above this one. You can or delete this row after you are done adding tasks.
| Total Budgeted Cost | 118630 | 1500 | 1500 | 6500 | 17500 | 17000 | 19375 | 55255
|  | Cumulative Planned Value (PV) | 1500 | 3000 | 9500 | 27000 | 44000 | 63375 | 118630
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 1500 | 3000 | 9500 | 24580 | 40580 | 59955 | 115210 | ← Enter the Actual Costs as calculated from the AC worksheet.
|  | Cumulative Earned Value (EV) | 1478.8 | 2957.6 | 8872.8 | 23660.8 | 38448.8 | 59152 | 109431.2 | ← Enter the Earned Value as calculated from the EV worksheet.
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -21.2 | -42.4 | -627.2 | -919.2 | -2131.2 | -803 | -5778.8
|  | Schedule Variance (SV = EV - PV) | -21.2 | -42.4 | -627.2 | -3339.2 | -5551.2 | -4223 | -9198.8
|  | Cost Performance Index (CPI = EV/AC) | 0.98587 | 0.98587 | 0.93398 | 0.9626 | 0.94748 | 0.98661 | 0.94984
|  | Schedule Performance Index (SPI = EV/PV) | 0.98587 | 0.98587 | 0.93398 | 0.87633 | 0.87384 | 0.93336 | 0.92246
|  | Estimated Cost at Completion (EAC) | 120330.6735 | 120330.6735 | 127015.7109 | 123238.6648 | 125205.6085 | 120240.4255 | 124894.5666

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1 | Domain Purchasing | 5000 | 100% | 100% | 100% | 100% | 100%
2 | Client Requirement | 6750 | 60% | 80% | 80% | 90% | 90%
3 | Purchasing a WordPress template | 12000 | 25% | 50% | 50% | 70% | 70%
4 | Other Expances (Photocopy) | 43880 |  | 85% | 85% | 85% | 85%
5 | Content Writing | 9000 |  | 40% | 68% | 82% | 82%
6 | Web Design | 28000 | 15% | 40% | 70% | 88% | 93%
7 | Graphic Design | 14000 |  |  | 85% | 85% | 85%
8 | Final Review | 0
- | -
- | -
- | -
Insert new rows above this one
|  | Cumulative EV | 16250 | 68498 | 91318 | 100693 | 102093

## AC
Actual Cost Worksheet
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5
1 | Domain Purchasing |  | 4200
2 | Client Requirement |  | 3000 | 1500 |  | 750
3 | Purchasing a WordPress template |  | 850 | 925 | 0 | 990 | 0
5 | Other Expances (Photocopy) |  | 0 | 625 | 0 | 0 | 0
5 | Content Writing |  | 0 | 4000 | 2000 | 2000 | 0
6 | Web Design |  | 5000 | 10000 | 10000 | 2000 | 3000
7 | Graphic Design |  |  |  | 8500 | 0
8 | Final Review
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 13050 | 17050 | 20500 | 5740 | 3000
|  | Cumulative Actual Cost (AC) | 13050 | 30100 | 50600 | 56340 | 59340

## ©
Earned Value Management (EVM) Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/critical-path-method.html
© 2012-2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.