## Issue Register
ID | Title | Type | Status | Date Raised | Last Update | Closure Date | Raised by | Owner | Actionee | Cause | Event | Effect | Probability | Impact (monetary) | Proximity | EV | Importance | Response(s) | Description
1 | Medical | Etc. | Closed | 2022-02-11 | 2022-02-25 | 2022-02-25 | Adithya Narasinghe (PM) | Kanishka Gimhan (RM) | Kanishka Gimhan (RM) | unable to perform their duties due to covid-19 infection. | If the remain team members do not come up with a plan to handle the additional workload. | This affects the smooth continuation of the project, which will delay the system deployment. | 50% to 75% | 55000 | This month | 0 | Medium | Accept | As this risk is high, continue to use virtual approaches for conferences and cloud services to continue the work. Reassign the allocated responsibilities to another group member or distribute the tasks among all available members
2 | Technical | Etc. | Closed | 2022-02-19 | 2022-03-01 | 2022-03-24 | Adithya Narasinghe (PM) | Kanishka Gimhan (RM) | Kanishka Gimhan (RM) | Planned technology stack might not support all the features that are in the scope | If the team is unable to find a solution. | There are some incompatibilities that can only be identified while developing the system. | 25% to 50% | 40000 | This month | 0 | Low | Accept | As this risk is low, changing the technology stack or adjusting the scope to what’s technically feasible with the current technology stack.
3 | Technical | Etc. | Active | 2022-02-19 | 2022-03-25 |  | Adithya Narasinghe (PM) | Kanishka Gimhan (RM) | Adithya Narasinghe (PM) | System Overload | If the team does not focus on the issue. | Negatively impact the system development, performance or stability. | 75% to 100% | 20000 | Next 3 months | 17000 | High | Active | As this risk is high, evaluate the conditions and figure out contingencies and sort that on a case by case by case basis
4 | Technical | Etc. | Active | 2022-02-19 | 2022-03-23 |  | Lawantha Bandara (QM) | Kanishka Gimhan (RM) | Adithya Narasinghe (PM) | After the deployment, the demand for the website can be much higher than the initial expectations | If team developers does not solve issue ASAP. | Website running slow or not functioning at all | 50% to 75% | 8000 | This month | 5000 | Medium | Active | As this risk is medium, monitor the website traffic after the deployment and upgrade the plan or migrate the website to a different service provider
5 | Team Performance | Schedule | Active | 2022-02-19 | 2022-03-25 |  | Sonali Silva (Startup) | Kanishka Gimhan (RM) | Helani Jayawardena (SM) | Frequent power failures in Sri Lanka impacting the team's performance. | If the team does not focus on the issue. | The project deadlines will not be met. | 75% to 100% | 100000 | Next 3 months | 87000 | Medium | Active | As this risk is medium, adjust all tasks around the Ceylon Electricity Board's published power outage timing schedule.
6 | Financial | Legal | Closed | 2022-02-19 | 2022-03-23 | 2022-03-25 | Helani Jayawardena (SM) | Kanishka Gimhan (RM) | Sonali Silva (Startup) | Instability of the rupee value | If the team does not focus on the issue. | The project costs will be higher than the initial estimates. | 75% to 100% | 25000 | Next 3 months | 0 | High | Accept | As this risk is high, make all necessary subscriptions in advance without delaying
7 | Technical | Etc. | Active | 2022-03-01 | 2022-03-18 |  | Adithya Narasinghe (PM) | Kanishka Gimhan (RM) | Kanishka Gimhan (RM) | The DBMS requires more main memory and disk storage. | If the team does not focus on the issue. | The database cannot be installed. | 25% to 50% | 8000 | This month | 3000 | Low | Active | As this risk is low, check the server bandwidth, storage and proceed.
8 | Technical | Etc. | Closed | 2022-03-01 | 2022-03-11 | 2022-03-18 | Kanishka Gimhan (RM) | Kanishka Gimhan (RM) | Adithya Narasinghe (PM) | WooCommerce Doesn’t Work with Every Theme. | If team developers does not solve errors ASAP. | There are some incompatibilities that can only be identified while developing the system | 25% to 50% | 12000 | This month | 0 | Low | Accept | As this risk is low, changing the technology and theme.
9 | Technical | Etc. | Closed | 2022-03-09 | 2022-03-23 | 2022-03-25 | Helani Jayawardena (SM) | Kanishka Gimhan (RM) | Lawantha Bandara (QM) | Clashing with other functions | If the team does not focus on the issue. | This can have a significant influence on the accuracy of system data, limiting system capacity to adjust and increase system marketing activities over time. | 25% to 50% | 25000 | This month | 0 | Low | Accept | As this risk is low, select the most suitable plugin and install it.
10 | Technical | Etc. | Active | 2022-03-09 | 2022-02-21 |  | Sonali Silva (Startup) | Kanishka Gimhan (RM) | Lawantha Bandara (QM) | The slow page load time. | If team developers does not solve issue. | It will affect buyers and other customers many times and display error messages | 50% to 75% | 60000 | Next 3 months | 38000 | Medium | Active | As this risk is medium, Remove all unused plugins and themes from the wordpress.
11 | Delay of the client | Etc. | Closed | 2022-03-16 | 2022-02-20 | 2022-02-20 | Sonali Silva (Startup) | Kanishka Gimhan (RM) | Sonali Silva (Startup) | The product list was not provided on time by the client. | If the team is unable to find a solution. | The team will deviate from the planned time schedule. | 50% to 75% | 15000 | This month | 0 | Medium | Accept | As this risk is medium, reschedule the workload according to the deadlines.
- - - - PRINCE2® Templates - - - -
A guide for this template, it’s latest version, and all other templates are available at mplaza.pm/templates
Also, you may be interested in using our PRINCE2 eLearning Courses available at mplaza.pm
Copyright 2018, Management Plaza
You can use this document for free in your projects and for your personal purposes. Redistributing this document or using it for training requires permission from Management Plaza.
This document is based on AXELOS PRINCE2® material. Reproduced under licence from AXELOS. All rights reserved.

## Definitions
Type | Probability Label | Probability value for EV | Proximity | Status | Importance | Importance threshold
Schedule | 75% to 100% | 87% | This month | Active | High | 10000
Quality | 50% to 75% | 63% | Next 3 months | Closed | Medium | 5000
Legal | 25% to 50% | 38% | Next 6 months |  | Low | 0
Etc. | 10% to 25% | 18% | Far away
| 5% to 10% | 8%
| 0% to 5% | 2.5%